## Cover Page & Intro
RISK REGISTER TEMPLATE
Prepared By: Awine Akanlerige
Title:
Healthcare Risk Register
Date:
[Insert Date]
Healthcare Risk Register Template
Date: March 18, 2026
This workbook is a healthcare-adapted risk register designed to document, assess, track, and monitor risks across patient care, privacy, cybersecurity, clinical operations, medical devices, and vendor-supported services.
Use the workbook to capture risks, assign likelihood and impact, record owners, track remediation actions, and support compliance, quality, and operational reviews.
Example healthcare scenarios covered in this version include EHR downtime, unauthorized access to patient records, medication safety issues, ransomware, specimen labeling errors, and medical device vulnerabilities.

## Lists
Likelihood | Impact | Treatment | Status | POC | Likelihood | Very Low | Low | Moderate | Major | Catastrophic
Very Low | Very Low | Mitigate | Open | Health Informatics | Very High | Moderate | Moderate | High | High | Critical
Low | Low | Transfer | In Progress | Privacy Office | High | Low | Moderate | Moderate | High | High
Moderate | Moderate | Accept | Monitoring | Clinical Engineering | Moderate | Low | Moderate | Moderate | Moderate | High
High | Major | Avoid | Closed | IT Security | Low | Low | Low | Moderate | Moderate | Moderate
Very High | Catastrophic |  |  | Pharmacy | Very Low | Very Low | Low | Low | Low | Moderate
Lab Manager
Nursing Leadership
Emergency Department Manager
Quality & Patient Safety
Facilities

## Instructions
INSTRUCTIONS FOR USE
This template contains multiple sheets that support risk identification, scoring, treatment, and monitoring in healthcare environments.
1. Risk Register:
This is the primary sheet for recording identified risks.
Fields include: Risk ID, Risk Description, Control ID/Subcategory, Implemented Controls, Likelihood, Impact, Risk Rating, Remediation Recommendations, Risk Treatment, POC, key dates, status, and notes.
Use this section to track risks related to patient safety, privacy, information systems, medical devices, staffing, and service delivery.
Instructions:
Enter one risk per row. Select Likelihood, Impact, Treatment, and Status from dropdown lists. Update records regularly as actions progress.
2. Threat Listing:
This sheet provides healthcare-relevant examples of cybersecurity, privacy, operational, clinical, environmental, vendor, and regulatory threats.
Use it as a reference when describing risks and considering possible consequences.
3. Risk Matrix Tool:
This sheet explains the scoring logic for likelihood and impact and shows how qualitative risk ratings are determined.
Use the matrix definitions when assigning values in the Risk Register.
4. Lists (Hidden):
This sheet stores dropdown values and lookup mappings used across the workbook.
Good practice in healthcare risk management:
Review risks with clinical, privacy, IT, quality, and operations stakeholders; ensure patient harm, regulatory exposure, service continuity, and reputational impact are all considered.

## Risk Register
Risk ID | Risk Description | Control ID / Subcategory | Implemented Controls | Likelihood | Impact | Risk Rating | Remediation Recommendations | Risk Treatment | POC | Date Identified | Scheduled Completion Date | Actual Completion Date | Status | Notes
HR-001 | EHR downtime delays medication orders and clinical documentation | IT-BCP / EHR Availability | Downtime procedures, backup access plan, on-call infrastructure support | High | Major | High | Test downtime workflow quarterly; strengthen failover monitoring and clinician communication | Mitigate | Health Informatics | 2025-03-18 | 2026-06-30 |  | Open | Priority risk for inpatient and ED workflows.
HR-002 | Unauthorized access to patient records / PHI | PRIV-ACC / Access Control | Role-based access, MFA, audit logs, privacy training | Moderate | Major | Moderate | Tighten access reviews, monitor anomalous access, refresh minimum-necessary guidance | Mitigate | Privacy Office | 2025-03-18 | 2026-05-31 |  | In Progress | Consider privileged-access reviews and break-glass oversight.
HR-003 | Barcode medication administration failure increases medication error risk | MEDSAFE / Medication Administration | Manual double-check workflow, nursing escalation pathway, device support | Moderate | Catastrophic | High | Improve scanner maintenance, add downtime checklist, review incident trends | Mitigate | Pharmacy | 2025-03-18 | 2026-05-15 |  | Open | Link to quality and patient safety review.
HR-004 | Ransomware disrupts clinical systems and scheduling | SEC-IR / Cybersecurity Incident Response | EDR, segmented network, backups, phishing training, incident response plan | High | Catastrophic | High | Run tabletop exercise, validate restore times, harden remote access controls | Mitigate | IT Security | 2025-03-18 | 2026-07-31 |  | Open | High operational and reputational impact.
HR-005 | Third-party vendor integration exposes patient data through misconfigured sharing | VEND-DATA / Vendor Management | Contract review, security questionnaire, access approvals, BA/PHIPA clauses | Moderate | Major | Moderate | Formalize vendor privacy review checklist and monitor data-sharing permissions | Transfer | Privacy Office | 2025-03-18 | 2026-06-15 |  | Monitoring | Applies to digital health and analytics vendors.
HR-006 | Specimen labeling mismatch leads to incorrect lab result attribution | LAB-QA / Diagnostic Safety | Two-identifier policy, barcode labels, lab rejection process | Low | Major | Moderate | Audit labeling compliance and refresh specimen collection training | Mitigate | Lab Manager | 2026-03-18 | 2026-04-30 |  | In Progress | Track near misses and rejected samples.
HR-007 | Connected medical device vulnerability affects availability or integrity | BIO-MED / Device Security | Asset inventory, patch coordination, network segmentation | Moderate | Major | Moderate | Perform device risk review; coordinate with vendor on patching and compensating controls | Mitigate | Clinical Engineering | 2026-03-18 | 2026-08-31 |  | Open | Includes infusion pumps and bedside monitoring devices.
HR-008 | Staff shortage or surge volumes delay triage and care escalation | OPS-WF / Workforce Capacity | Escalation policy, float staffing, surge protocols | High | Major | High | Review staffing triggers and escalation thresholds; update surge response plan | Accept | Nursing Leadership | 2026-03-18 | 2026-05-31 |  | Monitoring | Operational risk with direct patient access implications.

## Threat Listing
Threat Listing The table below provides healthcare-relevant threat examples to consider when evaluating risk to patient care, privacy, clinical operations, and supporting technologies.
Threat Source | Threat | Description | Consequences
Cybersecurity | Ransomware | Malware encrypts clinical or administrative systems and disrupts access. | Delayed care, cancelled appointments, downtime procedures, potential privacy incident.
Cybersecurity | Phishing / credential theft | User credentials are compromised through social engineering. | Unauthorized access, account misuse, potential PHI disclosure.
Privacy | Unauthorized record access | A workforce member or third party accesses PHI without a valid need. | Privacy breach, legal exposure, reputational harm, loss of patient trust.
Privacy | Misconfigured data sharing | Interfaces, shared drives, or vendor settings expose patient data. | Disclosure of PHI, regulatory reporting, contract and reputational risk.
Clinical Process | Medication administration error | Failure in barcode scanning, ordering, transcription, or verification. | Patient harm, adverse drug events, quality/safety review.
Clinical Process | Specimen labeling mismatch | Samples are mislabeled or linked to the wrong patient. | Incorrect results, treatment delays, repeat collection, patient safety event.
Medical Device | Connected device vulnerability | A device cannot be patched promptly or contains exploitable weaknesses. | Device unavailability, integrity concerns, clinical workflow disruption.
Operational | EHR downtime | Core documentation, ordering, or results systems become unavailable. | Manual workarounds, delayed care, reduced situational awareness.
Operational | Staff shortage / surge capacity failure | Workforce shortages or demand surges reduce safe coverage. | Delayed triage, wait times, quality issues, staff burnout.
Vendor / Third Party | Vendor outage or delayed support | A third-party platform or service becomes unavailable. | Scheduling disruption, delayed reporting, workflow bottlenecks.
Legal / Regulatory | Policy breach / non-compliance | Required controls, privacy practices, or documentation are not followed. | Audit findings, remediation burden, possible fines or sanctions.
Environmental | Power failure | Power loss affects systems, devices, refrigeration, or operations. | Service disruption, equipment failure, patient safety consequences.
Environmental | Temperature / humidity control failure | Improper environmental conditions affect labs, servers, or supplies. | Equipment damage, degraded performance, specimen or medication loss.
Managerial | Incomplete documentation | Policies, procedures, or recovery documentation are missing or outdated. | Inconsistent response, governance gaps, prolonged recovery times.

## Risk Matrix Tool
LIKELIHOOD & IMPACT DETERMINATION Values below are provided with healthcare-focused explanations to help assess the probability and consequence of risk events. |  |  | RISK CALCULATION The matrix below translates likelihood and impact into a qualitative rating.
Likelihood of Threat Event |  |  | Qualitative Risk Matrix
Qualitative Value | Suggested interpretation | Healthcare example |  | Impact
Very High | Expected frequently or under current conditions | Common control failure, repeated phishing, or known recurring outage pattern. |  | Very Low | Low | Moderate | Major | Catastrophic
High | Likely to occur in the normal operating environment | A realistic event seen periodically across departments or vendors. | Very High | Moderate | Moderate | High | High | Critical
Moderate | Possible and plausible but not frequent | A meaningful risk with some controls in place but clear residual exposure. | High | Low | Moderate | Moderate | High | High
Low | Unlikely but still credible | Would usually require multiple failures or unusual circumstances. | Moderate | Low | Moderate | Moderate | Moderate | High
Very Low | Rare under current controls | Possible in theory, but strongly constrained by current safeguards. | Low | Low | Low | Moderate | Moderate | Moderate
|  |  | Very Low | Very Low | Low | Low | Low | Moderate
Impact of Threat Events
Qualitative Value | Suggested interpretation | Healthcare example
Catastrophic | Severe patient, operational, legal, or organizational harm | Potential death or severe harm, system-wide failure, or major reportable privacy event.
Major | Serious adverse effect on care or operations | Significant service disruption, major financial loss, or material breach requiring escalation.
Moderate | Noticeable degradation or localized harm | Unit-level delays, repeat work, moderate safety/privacy exposure, or urgent remediation.
Low | Limited effect with manageable disruption | Minor workflow issue, quickly contained event, or near miss with limited consequences.
Very Low | Negligible effect | Minimal operational impact and little to no patient or privacy consequence.